## Sheet1
Project Name: Test Cases Report
UI Name: Web Application
Submitted By : Shaznina Mahrin Heya
ID: 203-50-038
Date : 06/10/24
Tracking ID | Module/Sub Module/Feature | Testing Date | Issue Findings | Priority | QA Status | QA Name | Attachments | QA Remarks | Reporting Manager's Feedback | Developer's comment | Current Iteration | Issue Occurance Count | Developer Name | Issue Status-Developers Feedback | Developer's Remark | Defect Solved Date
1 | User Login | 2024-06-06 | Ensure that a user can log in with correct username and password. | High | Solved
2 | User Login with Invalid Password | 2024-06-07 | Ensure that a user cannot log in with a valid username and an incorrect password. | High | Unsolved
3 | Password Reset | 2024-06-08 | Ensure that a user can reset their password. | High | Solved
4 | User Registration | 2024-06-08 | Ensure that a new user can register with valid information. | Medium | Unsolved
5 | User Registration with Existing Email | 2024-06-08 | Ensure that a user cannot register with an email that is already in use. | Medium | Solved
6 | Profile Update | 2024-06-11 | Ensure that a logged-in user can update their profile information. | Medium | Unsolved
7 | Logout | 2024-06-11 | Ensure that a logged-in user can log out of the application. | Low | Solved
8 | Search Functionality | 2024-06-11 | Ensure that the search functionality returns results for a valid query. | Low | Unsolved
9 | Add Item to Cart | 2024-06-12 | Ensure that a user can add an item to their shopping cart. | Medium | Solved
10 | Checkout Process | 2024-06-12 | Ensure that a user can complete the checkout process with valid payment information. | Medium | Unsolved